## Template
Final Year Project Timeline |  | WEEK 1 1/10/2018 | [6 empty] | WEEK 2 8/10/2018 | [6 empty] | WEEK 3 15/10/2018 | [6 empty] | WEEK 4 22/10/2018 | [6 empty] | WEEK 5 29/10/2018 | [6 empty] | WEEK 6 5/11/2018 | [6 empty] | WEEK 7 12/11/2018 | [6 empty] | WEEK 8 19/11/2018 | [6 empty] | WEEK 9 26/11/2018 | [6 empty] | WEEK 10 3/12/2018 | [6 empty] | WEEK 11 10/12/2018 | [6 empty] | WEEK 12 17/12/2018 | [6 empty] | WEEK 1 1/10/2018 | [6 empty] | WEEK 2 8/10/2018 | [6 empty] | WEEK 3 15/10/2018 | [6 empty] | WEEK 4 22/10/2018
Start Date: 03/10/2018 |  | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
Background/ State of the Art | 5 W
Apache pulsar | 1 d | bar: WEEK 1 1/10/2018 M to WEEK 4 22/10/2018 W; WEEK 6 5/11/2018 T to WEEK 7 12/11/2018 W; WEEK 8 19/11/2018 SU to WEEK 10 3/12/2018 SU
Mirai Botnet | 3 d | bar: WEEK 3 15/10/2018 W to WEEK 3 15/10/2018 SU; WEEK 7 12/11/2018 TH to WEEK 8 19/11/2018 SA
Latest Ddos attacks | 6 d | bar: WEEK 3 15/10/2018 TH to WEEK 4 22/10/2018 SA
Existing pub sub IDPS systems | 1 d | bar: WEEK 1 1/10/2018 M to WEEK 2 8/10/2018 TH
Network Virtualisation | 3 d | bar: WEEK 4 22/10/2018 M to WEEK 4 22/10/2018 SA; WEEK 11 10/12/2018 M to WEEK 2 8/10/2018 SU
SDN | 6 d | bar: WEEK 3 15/10/2018 TH to WEEK 4 22/10/2018 SA; WEEK 7 12/11/2018 M to WEEK 9 26/11/2018 SA
DDOS detection apps | 1 d
system enviroment setup | 3 d | bar: WEEK 1 1/10/2018 M to WEEK 3 15/10/2018 W
Pulsars current Security and assumptions | 6 d | bar: WEEK 3 15/10/2018 T to WEEK 7 12/11/2018 T
Development | 8 W
Set up Vms | 1 d | bar: WEEK 5 29/10/2018 M to WEEK 5 29/10/2018 TH
Set UP Ru , Mininet and Pulsar | 5 d | bar: WEEK 5 29/10/2018 W to WEEK 6 5/11/2018 W
Make One Subnet Network, talk to pulsar | 5 d | bar: WEEK 6 5/11/2018 T to WEEK 9 26/11/2018 TH
Use DDos Detection to detect malicicious info | 5 d | bar: WEEK 8 19/11/2018 M to WEEK 10 3/12/2018 M
Trigger Events based on attacks and shared maliciious info | 5 d | bar: WEEK 9 26/11/2018 F to WEEK 12 17/12/2018 W
Add Another subnet Network | 5 d | bar: WEEK 11 10/12/2018 SA to WEEK 3 15/10/2018 SU
Pass maclisous info between pulsar | 5 d | bar: WEEK 1 1/10/2018 TH to WEEK 4 22/10/2018 SA
Look at antiSpoofing | 5 d
Add 3rd Network and look at multi attacks | 5 d
Use Plsar in a Distrubted Network | 5 d
Test Phase | 3 W
test Apach pulsar setup | 1 d
Test 1 Subnet can send signals to pulsar | 5 d
Make One Subnet Network, talk to pulsar | 5 d
Malicious info send to pulsar ( One Subnet) | 5 d
Malicious info send to pulsar ( two Subnet) | 5 d
Two attacks on same subnet | 5 d
attacks at same time on different subnet | 5 d
Load processing testing of under heavy attack | 5 d
Test Third Network communication with malicious traffic to protect both | 5 d
malicious traffic on 2/3 | 5 d
Malcious Traffic on al | 5 d
Analysis | 8 d
7 d
2 d
2 d
1 d
1 d
Design Review / Phase 2
Demo Development
WriteUp

## Month 1
Project Title... |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4
Start Date: |  |  | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
DEVELOPMENT |  | 5 d
Finalize Script | owner | 2 d
Attachments | owner | 3 d
Financing | owner
PRE-PRODUCTION |  | x d
Casting | owner
Set Design | owner
Locations | owner
Costumes | owner
Hair | owner
Make-up | owner
PRODUCTION |  | x d
Rehearsals | owner
Principal Photography | owner
Second Unit | owner
POST-PRODUCTION |  | x d
Editing | owner
VFX | owner
Scoring | owner
Sound Editing | owner
Color Grading | owner
DISTRIBUTION |  | x d
Distribution Deals | owner
Marketing Push | owner
Press Tour | owner
Premieres | owner
ANNOTATIONS |  |  | WEEK 4 TH: Blocked out event
Blocked out phase
[26 empty] | N | Dependency
[26 empty] | n | Dependent Event
#NAME? |  | Modern Production Management Software. Create production calendars, breakdowns, call sheets & more on studiobinder.com | WEEK 4 T: © 2017 - StudioBinder